## Sheet1
Northwest Nebraska Development Corporation Chadron, NE
NNDC 2022 Strategic and Action Plan
Strategy/Action | Timeline | Budget/Source | Responsible Person(s) | Date completed | notes
A. Maintain & Diversify the Economy |  | Overall NNDC Operating Budget is $89,940
1. Existing Business visitation
Select businesses to call on | 3-4 monthly | staff time | Executive Director
Make calls monthly |  | staff time | Executive Director
Marketing NNDC to all businesses
2. Workforce development
PRIORITY: Support and recruitment of blue-collar trades
identify needs for skilled labor | as needed |  | Executive Director
identify ways to help deliver apprenticeships, OJT, other job shadowing |  |  | Executive Director & Board
Strengthen Internship Opportunities
Apprenticeships - RHOP for blue collar - Trades businesses - (Note: paperwork for apprenticeship can be challenging)
Collaboration between trades, CSC, WNCC, Community colleges
Retain or recruit young adults to area
CSC transcripted credit at a discounted rate
More WNCC connections in the community, more courses available in community (may need space)
3. Develop Target Markets
Define and identify businesses/clusters to target: Rail repair, niche retail, hospitality,eating establishments, agriculture related business, brewery |  | staff time | Ex. Dir. &Board |  | make cold calls, participate in Rural Prosperity task forces
Develop and print materials such as Brochures, online info, incentives, available sites, update web site (new photos?) |  | $1000/NNDC operating budget | Executive Director, Board | continuing updates | new ad for 2022 tourism publication
Food, makerspace, gallery, ideas from Creative District engagement sessions
Value added Ag - Small animal/ meat processing - Eggs - Farmers Markets - Hospitality
4. Advocate for improvements in surface transportation and access
Represent Chadron on HEA Board: Attend Ports to Plains Alliance meeting when feasible (annual meeting, DC fly-in) Serve as Treasurer | chair HEA board | HEA budget pays for DC trip $500/NNDC Operating budget | Executive Director | ongoing | meet monthly
Attend HEA DC fly-in, Washington, DC | yearly | $2000/HEA Board | Ex. Dir., HEA Board members |  | on hold
Attend Ports to Plains Board meetings | quarterly | staff time | Executive Director | as scheduled | currently via ZOOM
Work with existing railroads to enhance their profitability | as needed | $100/NNDC Operating budget | Executive Director | as requested
5. Promote maintenance of Chadron Community Airport
Promote commercial and private use of airport | participate on EAS selection | 0 | Board, Executive Director
Support city maintaining modern, safe facility | as needed | 0 | Board, Executive Director | as needed
Speak with US Senators, Representatives regarding EAS re-authorization | February | staff time | Executive Director
B. Enhance visibility and credibility of organization
1. Develop a plan to increase membership
Identify potential members, out of town as well as in Chadron, create list |  |  | Board, Executive Director
PRIORITY: Expand membership - Gordon businesses - Discount membership for first year - Convince loan clients to be members - Increase memberships through banking
PRIORITY: Cultivate home grown stories and promote through opportunities above
PRIORITY: Draft organized visibility plan and campaign - Explore non-profit Google marketing campaign - Connections to CSC or CHS alumni and publications - Target Business owners who have used NNDC loans - Personal business stories - Cultivate home grown stories
2. Maintain Economic Development Coordinator and office
PRIORITY: Hard look at new funding sources and identifying opportunities, re-write job description and plan for retirement transition
Continue educational training for Executive Director |  | $2500/NNDC operating budget | Executive Director
Attend NPPD, DED briefings | when scheduled | $200/NNDC operating budget | Executive Director
Communicate with members, outside public through newsletter, annual report, press releases, advertising | ongoing | $500/NNDC Operating budget | Executive Director | Quarterly newsletter, annual meeting
3. Cooperate with City Council & City Manager
Monthly presentations to City Council | 3rd Monday each month | 0 | Executive Director | ongoing | newsletter & monthly report to Crawford & Chadron Councils
Represent City at PADD board | 2nd Thursday each month | $1200 travel | Executive Director | ongoing
4. Maintain NE Certified ED Community requirements |  |  |  |  | due for renewal 2022
5. Host Governor's Pine Ridge Wild Turkey Hunt in October
Committee meetings ongoing, | monthly | staff time | Turkey Hunt Committee
Evaluate invitees, strive to get elected officials |  | staff time | Turkey Hunt Committee
Host VIP's for 2 day event |  | $11,000/Turkey Hunt Committee | Turkey Hunt Committee
C. Provide business tools and incentives
1. Market industrial land and vacant buildings
Maintain websites with listings - identify private land not listed | update monthly | staff time | Executive Director
2. Continue to operate/market revolving loan funds (LB840, USDA/RD RBEG , USDA/RD IRP)
Market available loan funds in newsletter, online, brochure, advertising, business visits | ongoing |  | Executive Director, NBDC
Continue to repay CDBG RLF to Dawes County | ongoing | staff time | Executive Director |  | paid semi annually, June and December
Work with Downtown Revitalization Task Force to fund completion of downtown plaza, Work with Chamber to develop Railroad Park Take advantage of Covid funding - Trails funding for Cowboy Trail to Chadron State Park |  | staff time | Executive Director and DTR Task Force | ongoing | work to identify grants, Community Foundation and city finance office to find funding for restrooms
3. Provide opportunities for business improvement
Work with WNCC for class schedule | ongoing | staff time | Executive Director |  | delivered online classes
Encourage new classes for Quick Books, EDGE by WNCC, send info to members | ongoing |  | WNCC and NBDC, Chamber
Continue to send webinar, federal assistance info for COVID assistance
4. Hold Leadership Chadron semi annually
Class graduated, surveys sent & returned, names gathered for recruitment forfuture classes |  |  | alums and Exec Director
Send invitation letters | July |  | Executive Director
D. Develop Affordable Housing
PRIORITY: NNDC as spark for housing - Stuart and Ansley examples - Land Bank - For profit investment club
1. Identify potential Housing locations, needs |  |  | City, Exec Dir. |  | Janet has list of infill lots, ideas for areas to target
Work with Janet to update Blight/substandard map | going to Planning Commission 3/14 |  | Deb, Janet, PADD
Assist with inquiries re: building apts. | when needed |  |  |  | Mike Works has inquired, new location may work better as it is already zoned R-3
Assist with RWFH grant by High Plains | resubmit in 2022 |  | Exec Dir., High Plains Director
Strategic Plan update held March 2, 2022
Black text indicates action items from 12/7/2021 plan
Green text indicates Gaps and Opportunities identified by NNDC strategic planning process
Orange text indicates Priorities identified by NNDC strategic planning process